## Completed
No | Area | Task | Result / evidence
1 | Security | Kaggle API token revoked in your account and verified | Token list empty; old token rejected; local copy deleted
2 | Security | Secrets kept out of git | .gitignore rules for kaggle / access_token / .env
3 | Audit | Whole project re-checked against files and tests | docs/PROJECT_AUDIT.md
4 | Segmentation | 17 videos split by patient (no leakage) | outputs/splits/video_splits.yaml
5 | Segmentation | Instrument model trained on GPU | Grasper Dice 0.852, L-hook 0.840 on unseen patients
6 | Segmentation | Tissue model trained on GPU | Mean Dice 0.735 on unseen patients (old 0.406)
7 | Segmentation | Reliability flag for every tissue | App shows 'tested' / 'NOT tested' next to each target
8 | Segmentation | Flicker reduction (smoothing) | Flicker -21 % tissue, -12 % instrument
9 | Tips | Your 40 human labels checked | 4 doubtful points excluded from scoring
10 | Tips | Grasper point definition agreed | Jaw hinge (your convention)
11 | Tips | Automatic labeller built | Matches your labels: L-hook 11.7 px, grasper 15.5-17.7 px
12 | Tips | New grasper method made default | Grasper error 128 px -> 31.9 px; L-hook 22.4 px
13 | Tips | Fallback for partly visible graspers | Risk 'Unavailable' 57/80 -> 10/80 frames
14 | Tips | Automatic labels for all frames except video01 | 6,800 frames from 16 videos
15 | DLC | DLC trained on machine labels (1 video) | Rejected: L-hook 339 px off
16 | DLC | DLC trained on automatic labels (1 video, 60 epochs) | Rejected: L-hook not found, grasper 40.7 px
17 | DLC | New DLC project from 16 videos | 1,190 frames, 85 clips, 16 videos
18 | DLC | DLC training dataset prepared | Ready; training started 20:53
19 | EndoVis | Robotic DLC model trained (79 epochs, GPU) | Held-out sequence: 81 % of joints found
20 | EndoVis | Official test videos found and downloaded | All 910 labelled test frames aligned
21 | EndoVis | Official test-set score | Median error 3.2 px; 79-92 % found on 4 of 6 videos
22 | Data | CholecSeg8k, all 17 videos | 32,320 files, duplicates checked
23 | Data | Endoscapes downloaded | 6.3 GB (adds cystic-duct labels)
24 | Data | Cholec80 checked | 75 GB, no masks -> not downloaded
25 | Pipeline | Motion, proximity and risk score | Working end to end
26 | Speed | CPU speed measured | 3.2 fps standard, ~7 fps fast setting (not real-time)
27 | App | Tested/untested badges, tidy notices, chart bug fixed | Checked live in Chrome
28 | App | Dashboard crash fixed | src/ui/training_monitor.py
29 | Demo | Motion analysis shown live in Chrome | Speed chart; tracking spikes on grasper 2 found
30 | Tests | Automated tests | 110 passing (13:30, incl. CVS, hybrid, auto-tip, UI tests); legacy 3 pass / 2 skip
31 | Docs | Full list of work + before/after comparison | docs/ALL_WORK_DONE.md
32 | Safety | Watchdog + GPU-only rule | DLC training at low priority, 8 of 16 CPU cores
33 | Status board | Readable status tables (web pages + Excel) | status/ folder
34 | DLC | L-hook-balanced training set (v2) built | 1,387 frames; L-hook examples 246 -> 711; 16 videos
35 | DLC | DLC #4 trained (16 videos, 30 epochs) and scored on your 40 frames | L-hook 45.8 px (from 243 px at ep20), grasper 64.8 px; current best still 22.4 / 31.9 px
36 | DLC | DLC v2 epochs 45/50 measured on your 40 frames; best checkpoints backed up | Grasper 17.5-18.9 px (beats 31.9 px); L-hook 34.7 px (ep45) / 249 px (ep50); outputs/models/dlc_v2_keep
37 | Safety | Auto-restart supervisor (Windows task, every 5 min) | Ran all night; removed by you on 2026-10-11 (schtasks /Delete)
38 | DLC | Overnight autopilot: settling + hybrid test + decision | Choice: geometry_current (outputs/logs/autopilot_decision.json)
39 | Pipeline | Hybrid keypoint source (DLC on instrument, else geometry) | keypoints.source: hybrid; 4 unit tests; measured overnight
40 | DLC | L-hook labelling set prepared for human clicks | 120 frames, 6 videos (12,18,20,37,52,55), 20 clips; prism-tips-LHOOK-annotator-2026-10-11
41 | DLC | Your 120-frame L-hook labelling session checked | 96 saved (86 tips + 10 not visible); you vs automatic labels: median 11.8 px, no offset; masks miss the thin hook tip in some frames
42 | DLC | DLC v3 trained on your L-hook clicks + hybrid made the app default | L-hook 22.4 -> 18.4 px (grasper unchanged 31.9 px); DLC runs automatically for new videos; 108 tests pass
43 | DLC | Checkpoint averaging (epochs 105/110/115) tested | Hybrid L-hook 18.4 -> 17.5 px (within noise; 3x DLC time) - not adopted, script kept
44 | Data | Risk datasets checked (logged in) | IEEE iAE: no files uploaded; SAGES CVS: not public; CholecTrack20: needs your data-use agreement; Endoscapes CVS: used
45 | Safety model | CVS (Critical View of Safety) model trained on Colab T4 cloud GPU | Test mAP 0.510 on 40 unseen videos (C1 0.47, C2 0.44, C3 0.62); 60 s/epoch on T4
46 | DLC | Wider test on 2 held-out patients (video52/55, your 35 clicks) | DLC/hybrid L-hook 9.8 px, 35/35 found vs geometry 28.6 px, 25/35 (caveat: init model had seen these videos with auto labels)
47 | Safety model | CVS v2 (higher resolution + regularisation) - FINAL | Val mAP 0.528 (v1 0.484); test mAP 0.539 on 40 unseen videos (v1 0.510)
48 | Safety model | CVS model downloaded, verified on laptop, added to app/pipeline/video overlay | Laptop CPU re-score test mAP 0.5388 = Colab; outputs/models/cvs_resnet50/v2
49 | Docs | README final results banner | README.md
50 | Data | SurgBlood bleeding dataset downloaded (public test release) | 886 frames, 20 clips, surgeon-reviewed bleeding masks
51 | Measurement | Approximate mm from 5 mm shaft width (*_mm_approx columns) | Labelled +-30-50 %; px stay primary; 2 unit tests
52 | Clinical | Clinical review package + fillable sign-off form | docs/CLINICAL_REVIEW_PACKAGE.md, docs/clinical_review_form.html
53 | DLC | Provenance audit of all DLC models | Fold model init (v2) had seen video52/55 -> earlier 9.8 px optimistic; outputs/label_qa/provenance.json
54 | Labelling tool | Grasper instructions corrected to jaw hinge | src/ui/label_tips.py
55 | Tips | Wider grasper test (your 44 clicks, 5 videos) | Geometry hinge 66.9 px median, 40/44 found (video01: 31.9 px). Scale-aware variant worse; not adopted
56 | Safety model | Bleeding detector (SurgBlood, Colab T4) | Test (4 unseen clips): detection F1 0.937, AUROC 0.942, region Dice 0.671
57 | DeepLabCut | CLEAN leakage-free L-hook test (video52/55 never in training) | DLC-only 6.5 px median, 35/35, 91 % within 20 px (docs/DLC_CLEAN_EVALUATION.md)
58 | Tissue | DSAD fine-tune on Colab T4 (false liver on other surgeries) | DSAD test 0.380 -> 0.846; appendicectomy liver 9.9 % -> 4.6 %; NOT adopted (CholecSeg8k 0.735 -> 0.697)
59 | Safety | Watchdog GPU cool-down cycle | 240 s run / 45 s pause; laptop stayed on through the DLC run
60 | Tests | Full test suite | 112 passed
61 | Tissue | Guarded local retrain (full data, gallbladder guard) | Guard never met; CholecSeg8k 0.696 vs 0.735 -> NOT adopted; default unchanged
62 | App | Surgery-type switch (gallbladder vs other tissue model) | configs/pipeline.yaml tissue.by_surgery; app sidebar
63 | Safety | Bleeding detector in pipeline + app | SurgBlood held-out clips 131/133 bleeding frames flagged; 0 false flags on appendicectomy video
64 | UI | React web app (draft) on :8510 with FastAPI backend | Synced video/timeline, events, flags, compare, stop, tissue annotation options, light/dark
65 | UI | Browser test suite (Playwright + axe) | 20 tests passing: every control, 4 screen sizes, WCAG 2 AA
66 | Speed | Model caching + stoppable DLC first run | Settings change starts in 0.3 s (was 10-20 s); Stop in ~0.2 s
67 | Sharing | Public link via Cloudflare quick tunnel | Temporary URL, full access (user choice)
68 | UI | React web app made the main app (port 8510); Streamlit drafts retired | Landing page, AI panel, read-aloud, resizable panels; 21 browser tests pass
Last updated 2026-10-12 23:33

## In progress
No | Task | Started | Progress | Where to watch | Expected finish
Last updated 2026-10-12 23:33

## Pending
No | Priority | Task | Waiting for | Estimate
1 | Low | Test tissue model on Endoscapes (new patients, cystic duct) | GPU to be free | 1 h
2 | Low | Retry TipNet heatmap network (paused) | DLC result | 1-2 h GPU
3 | Blocked | Confirm risk event definitions | Clinical review | -
4 | Blocked | Distances in mm instead of pixels | Camera calibration / depth data | -
5 | Blocked | Clinical sign-off: surgeon fills docs/clinical_review_form.html | Surgeon | -
6 | High | Grasper: scale-aware jaw length + grasper DLC on human hinge clicks | Next session | 2-3 h
7 | Low | Grasper learned model | ~100 human jaw-hinge clicks | -
8 | Low | Clinical sign-off | Surgeon fills docs/clinical_review_form.html | -
9 | Medium | Permanent public URL | Your devtunnel / ngrok / Cloudflare account login | 10 min
Last updated 2026-10-12 23:33

## Before vs now
No | Area | Before (earlier work) | Now (our work) | Change
1 | Instrument segmentation | Wrong target, Dice 0.26-0.32 | Grasper 0.852, L-hook 0.840 (unseen patients) | About 3x better
2 | Tissue segmentation | None | 7 tissues, mean Dice 0.735 (unseen patients) | New
3 | Training data | 1 video | 17 videos, split by patient | 17x more
4 | Tissue reliability | None | Each tissue marked tested / not tested | New
5 | Flicker | Not handled | -21 % tissue, -12 % instrument | New
6 | Instrument tip tracking | None | L-hook + up to 2 graspers tracked | New
7 | Tip accuracy (your 40 frames) | None | L-hook 18.4 px (DLC hybrid), grasper 31.9 px (was 128 px) | New; grasper 4x better
8 | Tip labels | None | 40 by you + 6,800 automatic (16 videos) | New
9 | DeepLabCut | None | DLC v3 (trained on your clicks) now improves the app L-hook 22.4 -> 18.4 px | In use
10 | Motion analysis | None | Speed, direction, gap handling, camera motion | New
11 | Proximity | None | Pixel distance to tissue, with safety flags | New
12 | Risk score | None | Rule-based with explanations; learned model locked until expert labels | New
13 | Pipeline | Notebooks only | Video in -> annotated video + CSV/JSON out | New
14 | Apps | None | Main app, dashboard, 2 labelling tools, status board | New
15 | CPU speed | Not measured | 3.2 fps standard, ~7 fps fast (not real-time) | Measured
16 | GPU use | None | AMD RX 6800M for all training | New
17 | Robotic test (EndoVis) | None | Official test: median 3.2 px | New
18 | Datasets | None | CholecSeg8k 17 videos, EndoVis train+test, Endoscapes | New
19 | Tests | 5 tests, 2 failing | 110 passing | 20x more
20 | Documentation | 1 README | 9 docs + status board | Much more
21 | Security | API token exposed in chat | Revoked and verified | Fixed
22 | Laptop safety | None | Watchdog (heat / memory / battery) | New
23 | Learned safety model | None | CVS model, test mAP 0.539 on 40 unseen videos (surgeon labels) | New
24 | Cloud GPU | None | Google Colab T4 used (3.2x faster than first attempt) | New
Last updated 2026-10-12 23:33

## Tip methods vs your 40 frames
No | Tip method | Trained on | L-hook found | L-hook error (median) | Grasper found | Grasper error (median) | Verdict
1 | Old mask-tip rule | - (geometry) | 37/37 | 22.4 px | 49/49 | 128.3 px | Replaced for grasper
2 | New default: hinge geometry | - (geometry) | 37/37 | 22.4 px | 49/49 | 31.9 px | Previous default
3 | Automatic labeller (true masks) | - (geometry) | 37/37 | 11.7 px | 49/49 | 15.5-17.7 px | Used to make labels
4 | DLC #1 | 200 machine labels, 1 video | 14/37 | 339 px | 8/49 | 438 px | Rejected
5 | DLC #3 | 200 automatic labels, 1 video | 0/37 | - | 23/49 | 40.7 px | Rejected
6 | TipNet (own network) | 5,600 automatic labels, 13 videos | 0 | - | 0 | - | Paused (did not learn)
7 | DLC #4 | 1,190 automatic labels, 16 videos | 33/37 (conf 0.1); 2 confident at 11.4 px | 45.8 px (ep20: 243 px) | 37/49 (conf 0.1) | 64.8 px | Not adopted yet - improving; continues as v2
8 | DLC #5 (v2) | 1,387 auto labels, 16 videos, L-hook x3, continues from #4 | 37/37 (8 confident at 7.7 px, ep45) | ep45 34.7 / ep50 249 / ep60 226 / ep80 155 px (unstable) | 49/49 | ep45 18.9 / ep50 17.5 / ep60 69 / ep80 76 px | Finished ep80 - not better; settling phase running
9 | DLC final (v2 + settling) | 1,387 auto labels, 16 videos | 100% | 74.1 px | 100% | 97.1 px | measured overnight
10 | Hybrid (DLC on instrument, else geometry) | 1,387 auto labels, 16 videos | 100% | 22.4 px | 100% | 40.6 px | measured overnight
11 | Hybrid, DLC for grasper only | 1,387 auto labels, 16 videos | 100% | 22.4 px | 100% | 40.6 px | measured overnight
12 | Hybrid, DLC for L-hook only | 1,387 auto labels, 16 videos | 100% | 22.4 px | 100% | 31.9 px | measured overnight
13 | DLC #6 (v3) | 86 HUMAN L-hook clicks (6 videos) + auto grasper labels; continues from settled DLC | 37/37 | 69.6 px alone (ep110: 31.8) | 49/49 | 161.9 px alone | Used inside the hybrid
14 | HYBRID: DLC v3 for L-hook, geometry for grasper | 86 human L-hook clicks + geometry | 37/37 | 18.4 px | 49/49 | 31.9 px | NEW APP DEFAULT (best L-hook so far)
15 | Wider test: DLC hybrid on video52/55 (held out) | your clicks from 4 other videos | 35/35 | 9.8 px | - | - | vs geometry 28.6 px (25/35) on same frames; optimistic, see caveat
Last updated 2026-10-12 23:33